INFT 5028 — Daily Scrum Notes Capstone Project for Business Intelligence and Analytics

Meeting

| Team | Alpha | Date | May 6, 2026 |
| --- | --- | --- | --- |
| Scribe | Pham, Thanh | Facilitator | Dolinger, Patrick |

| Attendees | Pham, Thanh ¦ Mwangi, Ann ¦ Okoro, Chukwuma ¦ Ayide, Juliana |
| --- | --- |

Standup — three questions per member

Each member answers: (1) What did I complete since the last scrum? (2) What am I working on today? (3) What is blocking me?

| Member | Completed since last scrum | Today's plan | Blockers |
| --- | --- | --- | --- |
| Thanh, Pham | Work alongside the team to finalize the Panda EDA & predictive modelling Collecting & centralizing all members’ notebooks and docs to prepare for Checkpoint#2 | Team meeting to prepare outline for presentation Checkpoint#2 - Chuks presentation rehearsal - Check out all the requirements in Checkpoint#2 - Prepare Docs Deliverables W3 - Review GitHub to make sure all data is uploaded. | NA |
| Mwangi, Ann | Work alongside the team to complete the data modelling in Microsoft Power BI by the end of the day, ensuring the project structure includes: - A staging folder with staging tables - A dimension folder with dimension tables - A fact folder with fact tables Create a walkthrough video for team review, knowledge sharing, and reproducibility of the workflow. | Perform EDA and predictive modelling in Python to address key project deliverables, including: - Analyzing the distribution of age groups across health regions - Developing a correlation matrix comparing socioeconomic and health variables - Performing linear regression and polynomial trend fitting for 5–10-year population projections by age cohort - Creating visualizations, including seaborn heatmaps for regional health indicator comparisons - Exporting forecast tables as CSV files for import into Microsoft Power BI - Building a simple predictive model for chronic disease prevalence rate prediction - Documenting the methodology, data inputs, assumptions, and early findings/results Validated findings and modelling approaches with team members to identify the most effective direction for the next step |  |
| Okoro, Chukwuma | Collaborated with the team to finalize our data model structure, including staging, dimension, and fact tables | Performed exploratory data analysis, forecasting, correlation analysis, visualization development, and predictive modelling to support project deliverables, including documentation of methodology, assumptions, and preliminary findings. | N/A |
| Ayide, Juliana |  |  |  |

Blockers requiring instructor attention

Anything in the Blockers column above that the team cannot resolve internally — list it here so it carries over to the Thursday checkpoint.

Blocker 1: Blocker 2: Blocker 3:

Decisions & action items

| Decision / Action item | Owner | Due |
| --- | --- | --- |
| Review Checkpoint#2 with team members Performed EDA and predictive modelling in Python, validated results with team members to select the best approach for next steps | Thanh | May 6 |
| Performed EDA and predictive modelling in Python, validated results with team members to select the best approach for next steps | Ann | May 6 |
| Performed EDA and predictive modelling in Python, validated results with team members to select the best approach for next steps Align the Checkpoint#2 with all team members and prepare documents for presentation on Thursday. | Chucks | May 6 |
| Performed EDA and predictive modelling in Python, validated results with the team to select the best approach for next steps. | Juliana | May 6 |
| Presentation CHECKPOINT #2 | Chucks | May 7 |

Submit at Thursday checkpoint as evidence of daily standups.