## Required Deliverables_Full List
Required Deliverables
Required Deliverables — Full List
| Wk | Duration | Deliverable | Description | Due | Thursday Presentation Focus | Value/Evaluation/ Due Dates (if applicable)
| 1 | Apr 22 - 24 | Project Charter | Problem statement, stakeholder persona, success criteria, scope boundaries | End of Week 1 | No Thursday checkpoint this week (course begins Wed, Apr 22); scoping work only - D124
| 1 |  | GitHub Repository | Initialized repo with README, folder structure, .gitignore, team member access | End of Week 1
| 1 |  | Milestone Plan | 4-week sprint plan with target dates and success criteria per milestone | End of Week 1
| 2 | Apr 27 – May 1 | Cleaned Dataset | Committed to repo; all nulls, duplicates, type errors resolved; changes documented | End of Week 2 | Before/after data quality, schema walkthrough, SQL or Python proof of concept_POC (plus Week 1 charter/scoping) | CHECKPOINT #1 (Apr 30)
| 2 |  | Data Dictionary | All fields documented with name, type, source, description, and transformation notes | End of Week 2
| 2 |  | Cleaning Scripts (SQL or Python) | Commented SQL files and/or Python notebooks (with SQLite or RDBMS) committed to repo covering all cleaning steps | End of Week 2
| 3 | May 4 - 8 | Python Notebook | EDA + predictive model with markdown documentation; exported outputs for Power BI | End of Week 3 | EDA findings, model overview, assumptions, dashboard wireframe | CHECKPOINT #2 (May 7)
| 3 |  | Dashboard Wireframe | Sketch or digital mockup of planned Power BI pages and visual layout | Thu Week 3
| 4 | May 11 - 15 | Power BI Dashboard (.pbix) | Interactive dashboard with all pages, DAX measures, slicers, and drill-throughs; committed to repo | End of Week 4 | Live dashboard demo, DAX explanation, internal review log | CHECKPOINT #3 (May 14)
| 4 |  | Internal Review Log | Written peer feedback on dashboard from all team members | Thu Week 4
| 5 | May 18 - 22 | Final Project Report (PDF) | Complete project documentation: charter, data dictionary, analysis summary, user manual, lessons learned | Wed Week 5 | Full capstone demo, team/personal reflections, lessons learned, project closure | FINAL PRESENTATION (May 21)
| 5 |  | Archived GitHub Repo | All deliverables committed, repo tagged v1.0, commit history clean | Wed Week 5
| 5 |  | Individual Reflection | Written personal reflection: role, contributions, successes, areas for growth | Wed Week 5
| 5 |  | Peer Evaluation | Completed peer evaluation for each team member using provided rubric | Wed Week 5

## Course Outline (hidden)
COURSE OUTLINE & 5-WEEK OVERVIEW
Week/Unit | Theme | Topics/Description | Key Activites | Relevant Learning Outcome(s) | Thursday Presentation Focus | Value/Evaluation/ Due Dates (if applicable)
Week 1 (22-24 Apr) | Scoping & Setup | Team formation | Charter, roles, data acquisition, GitHub setup, methodology selection | 1 | No Thursday checkpoint this week (course begins Wed, Apr 22); scoping work only - D124
Project charter
Data acquisition
Week 2 (27 Apr – 1 May) | Data Wrangling | SQL / Python cleaning | Data cleaning (SQL or Python/SQLite), Power Query transforms, data dictionary, version control | 1,2 | Before/after data quality, schema walkthrough, SQL or Python proof of concept_POC (plus Week 1 charter/scoping) | CHECKPOINT #1 (Apr 30)
Power Query ETL
QA & version control
Audit & finalize
Week 3 (4-8 May) | Analysis & Modelling | Python EDA | Python EDA, trend analysis, predictive model, export outputs for Power BI | 1,2,3 | EDA findings, model overview, assumptions, dashboard wireframe | CHECKPOINT #2 (May 7)
Predictive modelling
Validate & export
Dashboard prep
Week 4 (11-15 May) | BI Dashboard | Initial build | Power BI build, interactivity, internal review, DAX documentation | 3,4 | Live dashboard demo, DAX explanation, internal review log | CHECKPOINT #3 (May 14)
Interactivity & review
Iterate & QA
Final sprint plan
Week 5 (18-22 May) | Final Delivery | Final polish | Polish, documentation, submission, rehearsal, project closure | 4,5 | Full capstone demo, team/personal reflections, lessons learned, project closure | FINAL PRESENTATION (May 21)
Rehearsal
Submit all deliverables
Cross-team debrief
Apr

## Milestone Plan & PICs
Week | Date | Deliverable | Task Description | Detailed Task Description | Role Owner | Status | Notes | Milestone Success Criteria
Week 1 | Apr 22 - 24 | Project Charter | Define problem, scope, stakeholders | * Identify business problem * Define project objectives (ML/BI goal) * Identify stakeholders (Instructor, users) * Define success criteria (accuracy, insights) * List assumptions & constraints * Define in-scope vs out-of-scope | PM_Thanh | 🟡 In Progress |  | Week 1 — Foundation & Setup Deliverables: Project Charter, GitHub Repository, Milestone Plan Success Criteria: + Project Charter clearly defines + GitHub repository is: Properly initialized, organized with folders (Docs, Data, Scripts, etc.). includes README.md and .gitignore. accessible to all team members + Milestone plan includes: weekly breakdown (Week 1–5) clear deliverables per week, realistic deadlines aligned with course timeline + Repo shows initial commits and version control activity
Week 1 | Apr 22 - 24 | GitHub Repo | Initialize repo, folder structure | * Create GitHub repository * Set folder structure: /data, /notebooks, /scripts, /dashboard , /docs * Add README.md (project overview) * Set version control rules * Upload initial files | PM_Thanh | 🟡 In Progress
Week 1 | Apr 22 - 24 | Milestone Plan | Create 5-week timeline | * Break project into 5 weeks, * Assign tasks to roles (PM, Data, BI, ML), * Define start/end dates. Identify dependencies & align with submission deadline | PM_Thanh | 🟢 Completed
Week 2 | Apr 27- May 1 | Cleaned Dataset | Clean nulls, duplicates, types | * Check missing values, handle nulls (drop/impute) * Remove duplicates, Fix data types * Standardize formats (dates, currency) * Validate cleaned dataset, Save cleaned version | SQL/ETL Analyst_Chuks | 🔵 Not Started |  | Week 2 — Data Preparation Deliverables: Cleaned Dataset, Data Dictionary, Cleaning Scripts Success Criteria: * Dataset is fully cleaned: no missing/null values (or handled properly), duplicates removed, data types corrected (numeric, date, categorical) * All cleaning steps are: reproducible in SQL or Python scripts well-commented and organized in repo. *Data Dictionary includes: every field name data type source transformation rules * Evidence of before vs after data quality improvement * Dataset is committed and version-controlled in GitHub
Week 2 | Apr 27- May 1 | Data Dictionary | Document fields & definitions | * List all columns, * define each column meaning * Specify data types, * add units (if applicable) * Identify target variable, * document derived fields | * QA/Documentation _Michael & * Data Lead_Ann | 🔵 Not Started
CHECKPOINT #1 - (Apr 30) |  | Before/after data quality, schema walkthrough, SQL or Python proof of concept_POC (plus Week 1 charter/scoping)
Week 3 | May 4 - 8 | Cleaning Scripts | SQL/Python scripts | * Write Python/SQL cleaning scripts, * odumlarize code (functions) * Add comments for clarity,* test script on dataset * Save scripts in repo | SQL/ETL Analyst_Chuks | 🔵 Not Started |  | Week 3 — Analysis & Modeling Deliverables: Python Notebook, Dashboard Wireframe Success Criteria: *Jupyter Notebook includes: clear EDA (charts, summaries, trends). Identification of key demographic insights. Data storytelling using markdown explanations * At least one model or analytical method is applied: regression, forecasting, or classification (if applicable) Outputs are prepared for Power BI (clean structure/exported tables) * Dashboard wireframe includes: layout of pages planned visualizations. KPI definitions * Clear explanation of assumptions and limitations included * Work is reproducible and well-documented in GitHub
Week 3 | May 4 - 8 | Python Notebook | EDA + forecasting model | EDA: Summary statistics, distribution plots, Outlier detection Correlation analysis, Key insights extraction, Modeling: Define target variable, Split train/test data, Train baseline model Try multiple models, Evaluate performance, Select best model. | Data Lead_Ann | 🔵 Not Started
CHECKPOINT #2 - (May 7) |  | EDA findings, model overview, assumptions, dashboard wireframe |  |  | All
Week 4 | May 11 - 15 | Dashboard Wireframe | Design layout | * Identify key KPIs, * Sketch layout (top/middle/bottom) * Define charts (line, bar, table), * Define filters (date, category) * Align with business questions, Validate with team | Reporting Lead_Julliana | 🔵 Not Started |  | Week 4 — Visualization & Validation Deliverables: Power BI Dashboard (.pbix), Internal Review Log Success Criteria: * Power BI dashboard is fully functional: multiple pages (overview + detailed views). Slicers and filters working correctly. DAX measures correctly implemented * Dashboard clearly communicates: demographic trends. Healthcare-related insights * At least one live/demo-ready version is available * Internal review log includes: feedback from all team members issues identified and improvements made * Dashboard performance is stable (no broken visuals or errors)
Week 4 | May 11 - 15 | Power BI Dashboard | Build full dashboard | * Import cleaned dataset, * Create measures (KPIs) * Build visuals: KPI cards, Trend charts, Distribution charts * Add slicers (filters), * Improve layout & UX * Test interactivity, * Final polish (colors, titles) | Reporting Lead_Julliana | 🔵 Not Started
CHECKPOINT #3 - (May 14) |  | Live dashboard demo, DAX explanation, internal review log |  |  | All
Week 5 | May 18 -22 | Internal Review Log | Peer feedback | * Create review log sheet, * Record issues found * Assign action items, *Track status updates * Review weekly progress, * Resolve issues before final | QA/Documentation_Michael | 🔵 Not Started |  | Week 5 — Final Delivery & Closure Deliverables: Final Report, Archived Repo, Reflection, Peer Evaluation Success Criteria: * Final report includes: full project documentation (charter → analysis → results), clear summary of insights and findings, user guide for dashboard usage, lessons learned section. * GitHub repository: fully cleaned and organized, tagged version (v1.0) all deliverables committed * Final presentation is: well-structured (story: problem → approach → insights → impact). Includes dashboard demo, delivered within time limit * Individual reflection includes: personal contribution, challenges faced skills developed * Peer evaluation completed for all team members
Week 5 | May 18 -22 | Final Report | Compile documentation | Write introduction * Describe dataset, * Summarize EDA findings, * Explain model approach, * Present results, * Include dashboard screenshots, *Add conclusion & recommendations, * Proofread and format | QA/Documentation_Michael | 🔵 Not Started
Week 5 | May 18 -22 | GitHub Archive | Finalize repo | * Clean repository structure, * Remove unused files * Update README (final version), *Add documentation * Upload final dataset & notebook, * Tag final version (v1.0) | PM_Thanh | 🔵 Not Started
Week 5 | May 18 -22 | Reflection | Individual reflection | * Describe your role, * What you contributed * Challenges faced, * Skills learned, * What you would improve | All | 🔵 Not Started
Week 5 | May 18 -22 | Peer Evaluation | Evaluate team members | * Evaluate each team member * Assess contribution level * Provide constructive feedback * Submit evaluation form | All | 🔵 Not Started
FINAL PRESENTATION - (May 21) |  | Full capstone demo, team/personal reflections, lessons learned, project closure |  |  | All

## Internal Review Log_QA.Docs
Week | Date | Deliverable Reviewed | Task Description | Detailed Task Description | Role Owner | Reviewer | Issues Identified | Action Items | Status | Notes
Week 1 | Apr 22 - 24 | Project Charter | Define problem, scope, stakeholders | * Identify business problem * Define project objectives (ML/BI goal) * Identify stakeholders (Instructor, users) * Define success criteria (accuracy, insights) * List assumptions & constraints * Define in-scope vs out-of-scope | PM |  |  |  | 🟡 In Progress
Week 1 | Apr 22 - 24 | GitHub Repo | Initialize repo, folder structure | * Create GitHub repository * Set folder structure: /data, /notebooks, /scripts, /dashboard , /docs * Add README.md (project overview) * Set version control rules * Upload initial files | PM |  |  |  | 🟡 In Progress
Week 1 | Apr 22 - 24 | Milestone Plan | Create 5-week timeline | * Break project into 5 weeks, * Assign tasks to roles (PM, Data, BI, ML), * Define start/end dates. Identify dependencies & align with submission deadline | PM | All |  |  | 🟢 Completed
Week 2 | Apr 27- May 1 | Cleaned Dataset | Clean nulls, duplicates, types | * Check missing values, handle nulls (drop/impute) * Remove duplicates, Fix data types * Standardize formats (dates, currency) * Validate cleaned dataset, Save cleaned version | SQL/ETL Analyst | All |  |  | 🔵 Not Started
Week 2 | Apr 27- May 1 | Data Dictionary | Document fields & definitions | * List all columns, * define each column meaning * Specify data types, * add units (if applicable) * Identify target variable, * document derived fields | * QA/Documentation & * Data Lead |  |  |  | 🔴 Late
CHECKPOINT #1 - (Apr 30) |  | Before/after data quality, schema walkthrough, SQL or Python proof of concept_POC (plus Week 1 charter/scoping) |  |  | All
Week 3 | May 4 - 8 | Cleaning Scripts | SQL/Python scripts | * Write Python/SQL cleaning scripts, * odumlarize code (functions) * Add comments for clarity,* test script on dataset * Save scripts in repo | SQL/ETL Analyst | All |  |  | 🔵 Not Started
Week 3 | May 4 - 8 | Python Notebook | EDA + forecasting model | EDA: Summary statistics, distribution plots, Outlier detection Correlation analysis, Key insights extraction, Modeling: Define target variable, Split train/test data, Train baseline model Try multiple models, Evaluate performance, Select best model. | Data Lead | All |  |  | 🔵 Not Started
CHECKPOINT #2 - (May 7) |  | EDA findings, model overview, assumptions, dashboard wireframe |  |  | All
Week 4 | May 11 - 15 | Dashboard Wireframe | Design layout | * Identify key KPIs, * Sketch layout (top/middle/bottom) * Define charts (line, bar, table), * Define filters (date, category) * Align with business questions, Validate with team | Reporting Lead | All |  |  | 🔵 Not Started
Week 4 | May 11 - 15 | Power BI Dashboard | Build full dashboard | * Import cleaned dataset, * Create measures (KPIs) * Build visuals: KPI cards, Trend charts, Distribution charts * Add slicers (filters), * Improve layout & UX * Test interactivity, * Final polish (colors, titles) | Reporting Lead | All |  |  | 🔵 Not Started
CHECKPOINT #3 - (May 14) |  | Live dashboard demo, DAX explanation, internal review log |  |  | All
Week 5 | May 18 -22 | Internal Review Log | Peer feedback | * Create review log sheet, * Record issues found * Assign action items, *Track status updates * Review weekly progress, * Resolve issues before final | QA/Documentation |  |  |  | 🔵 Not Started
Week 5 | May 18 -22 | Final Report | Compile documentation | Write introduction * Describe dataset, * Summarize EDA findings, * Explain model approach, * Present results, * Include dashboard screenshots, *Add conclusion & recommendations, * Proofread and format | QA/Documentation | All |  |  | 🔵 Not Started
Week 5 | May 18 -22 | GitHub Archive | Finalize repo | * Clean repository structure, * Remove unused files * Update README (final version), *Add documentation * Upload final dataset & notebook, * Tag final version (v1.0) | PM | All |  |  | 🔵 Not Started
Week 5 | May 18 -22 | Reflection | Individual reflection | * Describe your role, * What you contributed * Challenges faced, * Skills learned, * What you would improve | All |  |  |  | 🔵 Not Started
Week 5 | May 18 -22 | Peer Evaluation | Evaluate team members | * Evaluate each team member * Assess contribution level * Provide constructive feedback * Submit evaluation form | All |  |  |  | 🔵 Not Started
FINAL PRESENTATION - (May 21) |  | Full capstone demo, team/personal reflections, lessons learned, project closure |  |  | All

## Sources
Nova Scotia Open Data Portal - Health, economy, demographics, education
https://data.novascotia.ca
Statistics Canada - LFS, census, health surveys, economic indicators
https://www150.statcan.gc.ca
Halifax Regional Municipality - Transit, permits, 311 data, geographic layers
https://catalogue-hrm.opendata.arcgis.com
CIHI Open Data - Hospital, wait times, health workforce
https://cihi.ca/en/access-data-and-reports/open-data
Open Canada Federal Portal - Federal data discovery hub — all teams
https://open.canada.ca/data/en/datase

## Role Breakdown
Role | Week | Key Responsibilities | PIC
PM | 1 | Charter, repo setup, milestone plan | Pham, Thanh
PM | 2 | Track progress, manage risks | Pham, Thanh
PM | 3 | Coordinate analysis & design | Pham, Thanh
PM | 4 | Ensure dashboard completion | Pham, Thanh
PM | 5 | Final submission | Pham, Thanh
Data Lead | 1 | Explore data, define KPIs | Mwangi, Ann
Data Lead | 2 | Define schema, validate data | Mwangi, Ann
Data Lead | 3 | Guide EDA & modeling | Mwangi, Ann
Data Lead | 4 | Validate dashboard metrics | Mwangi, Ann
Data Lead | 5 | Write analysis summary | Mwangi, Ann
SQL/ETL Analyst | 1 | Inspect datasets | Okoro, Chukwuma
SQL/ETL Analyst | 2 | Clean & transform data | Okoro, Chukwuma
SQL/ETL Analyst | 3 | Support Python exports | Okoro, Chukwuma
SQL/ETL Analyst | 4 | Fix data issues | Okoro, Chukwuma
SQL/ETL Analyst | 5 | Finalize scripts | Okoro, Chukwuma
Reporting Lead | 1 | Review requirements | Ayide, Juliane
Reporting Lead | 2 | Explore dataset | Ayide, Juliane
Reporting Lead | 3 | Create wireframe | Ayide, Juliane
Reporting Lead | 4 | Build dashboard | Ayide, Juliane
Reporting Lead | 5 | Polish visuals | Ayide, Juliane
QA/Docs | 1 | Prepare templates | Okafor, Michael
QA/Docs | 2 | Create data dictionary | Okafor, Michael
QA/Docs | 3 | Review wireframe | Okafor, Michael
QA/Docs | 4 | Test dashboard | Okafor, Michael
QA/Docs | 5 | Compile final report | Okafor, Michael